## Sheet1
SN | Task | Assigned To | From Date | To Date | Status
1 | Data Migration of JGI
2 | Data Migration of Modern Slippers
3 | Recuritment System
4 | Tax Calculator
5 | Modern Slippers HR Requirements
6 | 15 minutes grace time while office in (if comes before 15 min should be approved)
7 | 5 min late in
8 | For worker: two break: Tea Break: 15 minutes and Lunch Break: 30 minutes
9 | For employee: 30 minutes Lunch Break (shift start from 10 AM)
10 | Standard Worker working hour is 7 AM to 3 PM with 4 hour of compulsory Overtime
11 | For night shift 2 hours as rest time
12 | In case last day of month is holiday then, adjust it in leave policy as in government
13 | Jawalakhel Group of Industries
14 | Leave: Validation in late post | ukesh
15 | Wages tracking system for daily basis and contract basis | need discussion
16 | Day off exchange | ukesh
17 | Travel advance and Travel expense verification with voucher generation | punam | completed
18 | Late Office in for two days a month leave | ukesh
19 | Family detail maintain | prabin
20 | Training Request and Training Call Process | prabin
21 | Reports | prabin
22 | Monthly Report
23 | Attendance Summary Report
24 | Late In Early Out Report
25 | Leave
26 | Fowardable days in leave table | need discussion
27 | Paid and unpaid flag in leave | punam | completed
28 | Default days in leave | ukesh
29 | Assign while creating profile | ukesh
30 | Service Type in leave assign | punam | completed
31 | Carry forward and leave opening import and export in system | punam | completed
32 | Travel
33 | Expense approval should reflect advance amount if taken | punam | completed
34 | Experience and Training History of employee should be maintained | prabin | continue
35 | Shift should have total hour and grace time for late in and early out | ukesh
36 | dll to import attendnace manually | ukesh
37 | Overtime approval system as leave assign | ukesh
38 | Loan Entry(apply) allow back date( bug) | punam | completed | ukesh need to check on payroll system
39 | Redesign Asset table and issue table | prabin
40 | nepali date and english date | punam